## PQR Summary
<This checklist should be reviewed and customised (if needed), when planning quality. The main purpose of the Quality Review Checklist is to support the Project Quality Reviewers when verifying if key project activities were performed as expected and identifying quality findings.>
Project Quality Review
| Organisation / Department: | CSIC / USAL
| Project Name: | GIRLS
| Project Owner: | Partnership
| Business Manager: | Partnership
| Solution Provider: | Partnership
| Project Manager: | Universidad de Salamanca (USAL)
| Project Quality Reviewer: | CSIC
| Review Date: | 2024-01-30
| Overall Score: | 91.87%
| Overall Project Quality Assessment | 0.9187
| Area | % of Quality Compliance | Score | Included?
| Scope | 89.44% | 89.44% | Yes
| Schedule | 84.78% | 84.78% | Yes
| Cost | 92.86% | 92.86% | Yes
| Quality | 93.93% | 93.93% | Yes
| Risk | 97.62% | 97.62% | Yes
| Issues & Decisions | 90.62% | 90.62% | Yes
| Communication | 100% | 100% | Yes
| Project Organisation | 100% | 100% | Yes
| Outsourcing | 94.44% | 94.44% | Yes
| Client Satisfaction | 75% | 75% | Yes
Scoring Legend:
0 | "No answer: nothing done.
5 | "Yes, Partially" answer: some work done, but not to the required/expected level.
10 | "Yes" answer. Meets requirements and expectations as per the PM² methodology.
1 to 10 | The questions started by "How well…?" should be answered by scoring the related activity from 1 to 10, meaning that 1 is "very poor", 5 is "average" (requirements are met) and 10 is "excellent" (material that can be referenced).
N/A | This check is not applicable to this project.
Overall Assessment Key:
0 |  | Critical /significant issues or major process non-compliance.
0.7 |  | Unless immediate action is taken, project may become red.
0.9 |  | No significant non-compliance foreseeable at this time.
Yes
No

## Recommendations
<This table should be used for documenting findings and recommendations on quality assurance and control activities. Note that the Project Core Team (PCT) should contribute to define the action plan and the Project Quality Reviewers should validate whether the plan is adequate to resolve the identified findings.>
ID | Findings | Impact | Recommendation | Action Details (effort & responsible)
1
2
3
4
5
6
7
8
9
10
Note on A4: The findings identifier. It should be numbered sequentially.
Note on B4: Short description of the non-conformity or opportunity to improve identified during the execution of quality assurance or quality control activities.
Note on C4: A numeric value denoting the severity / impact of the non-conformity / opportunity to improve. The possible values are: 5=Very high 4=High 3=Medium 2=Low 1=Very low
Note on D4: Description of the alternatives and approach to resolve the non-conformity or to implement the opportunity to improve.
Note on E4: Description of the recommended action, person responsible, steps, deliverables, timescale, resources and effort involved.

## Scope
Scope Management |  | % of Quality Compliance | 89.44% | 89.44%
|  | Answer | Score | Comments
Scope Initiating
1 | Are requestor needs clearly documented (description of the need, who is requesting and the justification / priority)? | Yes | 10 | The needs analisys was incldued in the proposal | Yes
2 | Is the scope description explicitly describing the outputs that will be IN and OUT of project scope? | Yes | 10 | We believe it is. The outputs are properly described. | Yes, Partially
3 | Is there a formal Scope Statement? | N/A |  | The scope is described, but that is not incldued in a specific document. | No
4 | Are the requestor needs mapped to features/deliverables? | Yes | 10 | The project results are in line with the needs. | N/A
5 | Are all deliverables clearly identified? | Yes | 10 | The project results are described in the proposal.
6 | Were the requestor and provider side involved in the description of project scope and deliverables? | Yes, Partially | 8 | In this project, both sides are the same, the requestor and the provider.
7 | How well are deliverables descriptions documented? (Scale: 0 lowest - 10 highest) | 8 | 8 | As far as we understood, Erasmus+ project could always be improved.
8 | Are project success criteria clearly identified? | Yes | 10 | This is included in the proposal.
9 | Can project success criteria be easily measured? | Yes | 10 | Indicators are included in the proposal.
10 | Has the Project Steering Committee (PSC) approved the Project Charter? | Yes | 10 | Afther singing the bilateral agreements, the project started.
11 | Are assumptions and constraints documented? | N/A | - | As far as we understood, for Erasmus+ projects this is no needed.
12 | Have project dependencies been identified and documented? | N/A | - | As far as we understood, for Erasmus+ projects this is no needed.
13 | Are acceptance criteria documented? | Yes | 10 | It is related with the scope, stakeholders and the people reached.
Scope Planning
14 | Can the project deliverables be easily tracked from the Project Charter to the Project Work Plan (WBS)? | Yes | 10 | Also the timetable facilitates the monitoring of deliverables.
15 | Has the project scope been clearly understood and agreed by the key stakeholders in the Planning Kick-off meeting? | Yes | 10 | The project scope was discuss during the kick-off meeting.
16 | Is the granularity of the WBS appropriate in regards to the project length/complexity? | Yes | 10 | There are 20 results that will be developed during 3 years.
17 | Is the Project Manager (PM) comfortable with the WBS? | Yes | 10 | The PM participated in the creation of the WBS.
Scope Change Control
18 | Is a documented change management process in place? | N/A | - | This is not needed for KA2 projects. The important thing is the final result, not the previous versions.
19 | Is a Project Change Management Plan documented? | N/A | - | This is not needed for KA2 projects. The important thing is the final result, not the previous versions.
20 | Is a Change Log maintained? | N/A | -
21 | Is the Change Log reviewed regularly e.g. weekly? | Yes, Partially | 5
22 | Are Change Control Meetings in place? | Yes, Partially | 5 | Follow-up meetings include the quality assurance of the project
23 | Is an escalation procedure for project changes documented and being followed? | Yes, Partially | 5 | All changes must be approved by the PSC
24 | Were all scope changes approved by the Project Owner (PO / Project Steering Committee (PSC)? | Yes | 10 | Documents final versions are approved by the PSC.
|  | 6 | 161

## Schedule
Schedule |  | % of Quality Compliance | 84.78% | 84.78%
|  | Answer | Score | Comments
Activity Definition
1 | Is there a Project Work Plan (WBS+effort & cost estimations+project schedule)? | Yes | 10 | These were included in the project proposal | Yes
2 | Is there a consolidated schedule (Gantt chart)? | Yes | 10 | Theh final version was inclued in the proposal. | Yes, Partially
3 | Can you link the activities back to WBS? | Yes, Partially | 5 |  | No
4 | Is the level of detail (granularity) of the schedule appropriate? | Yes | 10 |  | N/A
5 | Are relevant business implementation related activities on the schedule? | No | 0
6 | Are relevant project management activities on the schedule? | Yes | 10
7 | Do tasks / activities have documented start and end events? | Yes, Partially | 5 | In some cases, this is not needed. Some are one-off activities.
8 | Does all work activities have a measurable output? | Yes | 10 | This measure could be qualitative or quantitative
9 | Were external dependencies accounted for? | N/A | -
Activity Sequencing
10 | Is a Critical Path defined for the overall Project? | N/A | - | We defined a risk management, but not a critial path
11 | Is the Critical Path defined for each deliverable (iteration for PM²-Agile projects) as you initiated them? | N/A | -
12 | Is the Critical Path defined after consultation of the Project Core Team? | N/A | -
Activity Duration Estimation
13 | Were the estimations accurate until this moment? | Yes | 10
14 | Are estimations created by the team members who will implement the activities? | Yes, Partially | 5
15 | Was there a peer review of estimates? - By whom? | No | 0
16 | Was reference made (for estimating) to any previous similar project or previous phase of the project? - Which ones? | N/A | -
Schedule Development
17 | Was the schedule baselined? | Yes | 10
18 | Was the schedule baseline approved? | Yes | 10 | It was aproved in the proposal by the NA
19 | If re-baselined, was it done following the change management process? | Yes | 10 | The re-baselined was due to the delay in the approval and starting process.
Schedule Control
20 | Are tasks status / % of completion being tracked and documented? | Yes | 10
21 | Is the schedule (with iteration plan for PM²-Agile projects) regularly updated with actual velocity? | Yes | 10
22 | Is project on track regarding schedule (with iteration/sprint plan for PM²-Agile projects)? | Yes | 10
23 | Is the schedule reviewed regularly to consider project changes? | Yes | 10
24 | Is the critical path reviewed regularly? | N/A | -
25 | Are resources allocation checked weekly? | Yes | 10
26 | Are all the resources with the right amount of work (not over-allocated)? | Yes | 10
27 | Are internal and/or subcontractor resources delivering results per plan? | Yes | 10
28 | Are there regular reviews with internal and/or subcontractor resources? | Yes | 10
29 | Are project management processes being used with internal and subcontractor resources? | Yes | 10
|  | 6 | 195

## Cost
Cost |  | % of Quality Compliance | 92.86% | 92.86%
|  | Answer | Score | Comments
Resource Planning
1 | Is there a Resource Plan? | Yes | 10 |  | Yes
2 | Is the Resource Plan including all types of resources, including training needs? | Yes | 10 |  | Yes, Partially
3 | Can the Resource Plan be linked back to the WBS and schedule? | Yes | 10 |  | No
| Cost Estimating |  |  |  | N/A
4 | Was the current provider team involved in estimating? | Yes | 10
5 | Are subcontract commitments (deliverables and effort) written? | Yes | 10
6 | Are all project costs identified, including from requestor and provider side? | Yes | 10
7 | Was the WBS used to help cost estimating? | Yes | 10
8 | Are project management effort considered in project estimations? | Yes | 10
9 | Was the cost of risk identified? | Yes, Partially | 5 | Risks were indenfied, but not their cost.
Cost budgeting
10 | Has the budget been approved? | Yes | 10
11 | Has an appropriate payment schedule been defined? | Yes | 10
12 | Are there Purchase Orders (PO) for all authorized purchases and expenses? | Yes | 10
Cost control
13 | Are costs being actively managed? | Yes | 10
14 | Is the "percentage completed" (based on duration) accurate? | Yes, Partially | 5
|  | 0 | 130

## Quality
Quality |  | % of Quality Compliance | 93.93% | 93.93%
|  | Answer | Score | Comments
Quality Planning
1 | How well is the PM² methodology being used? (Scale: 0 lowest - 10 highest) | 8 | 8 | Some templates and procedures are not related to this project | Yes
2 | How well are the PM² templates being used? (Scale: 0 lowest - 10 highest) | 10 | 10 |  | Yes, Partially
3 | Is the Quality Management Plan understood by all? | Yes | 10 |  | No
4 | Have quality characteristics been established for the project? | Yes | 10 |  | N/A
5 | Is there a Quality Management Plan in place? | Yes | 10
6 | Was the Quality Management Plan approved by the Project Steering Committee (PSC)? | Yes | 10
7 | Is there a Deliverables Acceptance Management Plan? | Yes, Partially | 5 | This function is made by the PSC
8 | Is there an acceptance test plan in place? | Yes | 10
9 | Do all deliverables have acceptance criteria? | Yes | 10
10 | Is the acceptance test plan approved by the requestor? | Yes | 10
11 | Is a configuration management procedure in place (documented and implemented)? | Yes, Partially | 5
Quality Assurance
12 | Is the configuration management procedure being executed? | Yes | 10
13 | Is a project repository being maintained? | Yes | 10
14 | Is the project repository up to date? | Yes, Partially | 5
15 | Is the project considering a Project Quality Assurance (PQA) team/person? | Yes | 10
16 | Is quality being measured independently? | Yes | 10
17 | Are deliverables meeting their acceptance criteria? | Yes | 10
18 | When completed, have deliverables been accepted & signed-off? | Yes | 10 | Deliverables don't need to be signed
19 | Were the previous review recommendations implemented? | Yes | 10 | The only reviews were don by the evaluators before the project started
20 | Was a deliverables peer review conducted? | Yes | 10
21 | Were all project artefacts reviewed before sent to the requestor for approval? | N/A | -
22 | Are project plans regularly reviewed with the requestor? | N/A | -
23 | Have project/milestones/phase-exit reviews been performed with the requestor? | Yes | 10
24 | Are test specifications and test cases documented? | Yes | 10 | Surveys and questionnaires is the way to do this
25 | Will testing verify that all deliverables meet acceptance criteria? | Yes | 10 | The testing team is the PSC
Quality Control
26 | Are quality control activities taking place? | Yes | 10
27 | Have corrective actions been taken when required? | Yes | 10
28 | Are project quality reviews following the planned frequency and activities? | Yes | 10
29 | Are security & business continuity activities performed? | Yes | 10
30 | Is there a project configuration log? | Yes | 10
|  | 2 | 263

## Risk
Risk |  | % of Quality Compliance | 97.62% | 97.62%
|  | Answer | Score | Comments
Risk Identification
1 | Is there a Risk Management Plan? | Yes | 10 |  | Yes
2 | Were risks identified for this project? | Yes | 10 | The identification was made based on previous experiences in EU projects | Yes, Partially
3 | Is a Risk Log being used in the project? | Yes | 10 | This is mandatory in case the risks generate any problem | No
4 | Are requestor side and provider side involved in risk identification, including the Project Core Team (PCT)? | Yes | 10 |  | N/A
5 | Are the identified risks belonging to more than one risk category? | N/A | - | All risks are related to the project development
Risk Assessment
6 | Were risks quantified in terms of their risk level (likelihood & impact)? | Yes | 10
7 | Is risk assessment data accurate? | Yes, Partially | 5
8 | Is the risk impact on project budget assessed? | Yes | 10 | The Project coordinator wil decide about the budget
9 | Were all the risks approved as defined in the escalation procedure? | Yes | 10
10 | Were all the high and very high risks (risk level > 15) approved by the Project Steering Committee (PSC)? | Yes | 10
11 | Do you have a plan how to fund the risk actions? | Yes | 10
Risk Response Development
12 | Are all high and very high risks avoided or immediately reduced? | Yes | 10
13 | Are risk response strategies selected for each approved risk? | N/A | -
14 | Are contingency plans defined for accepted risks? | Yes | 10
15 | Are the actions related to the risk response strategies incorporated in the Project Work Plan? | Yes | 10 | The risk response strategies were cosidered in the initial project proposal
Risk Monitor & Control
16 | Is the Risk Log frequently revisited (at least weekly)? | Yes | 10
17 | Are risks discussed in Project Follow-up Meetings? | Yes | 10
18 | Are risks discussed in Project Core Team Meetings? | Yes | 10
19 | Are risks discussed in Project Review Meetings? | Yes | 10
20 | Are risks discussed in Project Steering Committee Meetings? | Yes | 10
21 | Are risks reviewed regularly (identification of new risks, assessment of the risk level and effectiveness of implemented actions)? | Yes | 10
22 | Is the risk log reviewed when changes are approved? | Yes | 10
23 | Are risk mitigation plans being carried out? | Yes | 10
|  | 2 | 205

## Issues & Decisions
Issues & Decisions |  | % of Quality Compliance | 90.62% | 90.62%
|  | Answer | Score | Comments
Issue Identification and Description
1 | Is an issue management process in place? | Yes | 10 | Risk management was defined in the roposal | Yes
2 | Is there an Issue Management Plan? | Yes | 10 | Risk management was defined in the roposal | Yes, Partially
3 | Is an Issue Log being used in the project? | Yes, Partially | 5 |  | No
4 | Are both requestor and provider side involved in issue identification? | Yes | 10 |  | N/A
5 | Is a Decision Log being used in the project? | Yes | 10
Issue Assessment and Action Description
6 | Are issues assessed in terms of urgency, impact and size? | Yes | 10
7 | Is issue assessment data accurate? | Yes | 10
8 | Is the effort of the issue-related action properly assessed? | Yes | 10
9 | Are actions selected for each issue? | Yes | 10
10 | Is a escalation procedure clearly defined for issues (based on urgency, impact and size)? | Yes, Partially | 5
11 | Are issue owners assigned to actions? | Yes | 10
12 | Are decisions following the defined escalation procedures for issues, risks and changes? | Yes | 10
Issue Monitor & Control
13 | Is the Issue Log reviewed at appropriate intervals? | Yes, Partially | 5
14 | How well is issues status monitored & reported? | Yes | 10
15 | Is the team closing issues in suitable time? | Yes | 10
16 | Is there any follow-up done on late items? | Yes | 10
|  | 0 | 145

## Communication
Communication |  | % of Quality Compliance | 100% | 100%
|  | Answer | Score | Comments
Communications Planning
1 | Is there a project contacts list (stakeholder matrix)? | Yes | 10 |  | Yes
2 | Does a Communications Management Plan exist? | Yes | 10 | It was included in the initial proposal, as part of the management work package (WP1). | Yes, Partially
3 | Are the expected project meetings and reports documented? | Yes | 10 | Each project meeting (online and onsite) has the corresponding agenda and minutes. | No
4 | Is the Communications Management Plan including all stakeholders? | Yes | 10 | Higher education teachers and students are the project stakeholders. | N/A
5 | Are the main stakeholders comfortable with the communication plan? | Yes | 10 | Higher education teachers and students are the project stakeholders.
Information Distribution
6 | Was an internal kick-off meeting conducted? | Yes | 10 | It took place in Salamanca, in Janary 2023.
7 | Is project status communicated to project stakeholders, including the Project Core Team (PCT) according to the Communication Plan? | Yes | 10
8 | Are Project Follow-up Meetings happening regularly? | Yes | 10 | Meetings are being held every 2 or 3 months.
9 | Are remote teams kept "in the loop" if applicable? | Yes | 10
10 | Are there regular Project Core Team (PCT) meetings? | Yes | 10
11 | Was an external kick-off meeting conducted? | Yes | 10
12 | Are the management/steering committee meetings happening as planned? | Yes | 10
Performance Reporting
13 | Are meeting minutes published after meetings? | Yes | 10
14 | Do meetings and reports follow the planned frequency? | Yes | 10
15 | Are the communication items (reports, meetings, others) customized for the intended audience (stakeholders)? | Yes | 10
Escalation Management
16 | Is a documented escalation process in place & understood? | N/A | -
17 | Is it being used effectively? | N/A | -
18 | Were escalation results been satisfactory(if any)? | N/A | -
|  | 3 | 150

## Project Organisation
Project Organisation |  | % of Quality Compliance | 100% | 100%
|  | Answer | Score | Comments
Organization & Planning
1 | Are project roles & responsibilities defined and documented? | Yes | 10 | They are properly documented in the proposal. | Yes
2 | Is there a Project Organization chart with all interfaces? | N/A | - | It is not necessary for the correct development of the project. | Yes, Partially
3 | Is a Project Steering Committee in place? | Yes | 10 | Yes, it is made of the partners coordinators. | No
4 | Are subcontracting resources properly used (if applicable)? | Yes | 10 | Only 2 things were subcontracted: the App and the creation of the project logo and image. | N/A
5 | Has the Project Core Team (PCT) the technical ability to get the work done? | Yes | 10 | The PCT has the technical skills and competencies for the work.
6 | Are there sufficient and appropriate resources to meet requirements? | Yes | 10 | All partner's teams are appropiate.
Staff Acquisition
7 | Were subcontracting members properly screened / selected? | Yes | 10 | The coordinator's staff is involved in these issues.
8 | Was an approved resourcing mechanism/agreement used? | Yes | 10 | The mechanism is defined by the Project Cordinator (USAL)
9 | Are evaluation criteria defined for project staff / subcontractors? | Yes | 10 | Each partner organization has its own evaluation criteria.
Team Development
10 | Is the level of cooperation between off-site & on-site teams satisfactory for the Project Manager (PM)? | Yes | 10 | It is working properly.
11 | Were teamwork issues handled correctly? | Yes | 10 | Until now, the team work is perfect.
12 | How satisfied are the team members with the project (scale: 0 lowest - 10 highest)? | 10 | 10 | The are satisfied with the project.
|  | 1 | 110

## Outsourcing
Outsourcing |  | % of Quality Compliance | 94.44% | 94.44%
|  | Answer | Score | Comments
Outsourcing Planning
1 | Are the outcomes of the contract well understood? | Yes | 10 | Only 2 things will be convered by an outssourcing contract: the App and the creation of the project logo and image. | Yes
2 | Is there an Outsourcing Plan? | N/A | - | As detailed above, is not necessary. | Yes, Partially
3 | Is there a concrete outputs delivery schedule? | Yes | 10 | This schedule was included in the original proposal. | No
4 | Are project management processes and quality controls to be followed by the outsourcer documented? | Yes, Partially | 5 | The goals of the products are clear and documented, but not the specific results from the outsourcing. | N/A
5 | Is the outsourcer evaluation criteria (services and deliverables) clearly defined? | Yes | 10
Outsourcing Contract Administration
6 | Was the contractor chosen according to the corporate processes and standards? | Yes | 10 | The coordinator has its own rules for contracting external services.
7 | Are signed contracts in place? | Yes | 10 | Yes, the coordinator project's office takes care of this.
8 | Were contracts reviewed by legal (or standard)? | Yes | 10 | The international project office and the accounting office reviewed it.
9 | Are SLAs defined in the contract? | Yes | 10 | The outsourcing contract was needed for the App and the creation of the project logo and image.
10 | How well were any internal agreements documented? | Yes | 10 | As these contracts are mandatory for the coordinator, all of them are well documented.
|  | 1 | 85

## NA Satisfaction
Client Satisfaction (Scale: 0 lowest - 10 highest) |  | % of Quality Compliance | 75% | 75%
|  | Answer | Score | Comments
1 | How satisfied is the NA with the schedule (allowing for Change Requests)? | 10 | 10 | The evaluation of the proposal was good. | Yes
2 | How satisfied is the NA with requirements? | 10 | 10 | The evaluation of the proposal was good. The requirements are correct. | Yes, Partially
3 | How satisfied is the NA with the quality of deliverables? | 10 | 10 | We fullfilled all the requirements included in the proposal | No
4 | How satisfied is the NA with project communication? | 5 | 5 | After the evaluation, this mark could change to 10. | N/A
5 | How satisfied is the NA with the technical ability of the Project Core Team (PCT)? | 5 | 5 | After the evaluation, this mark could change to 10.
6 | What is the overall client/requestor satisfaction? | 5 | 5 | After the evaluation, this mark could change to 10.
|  | 0 | 45

## Ammendments (hidden)
Description of Issue | Raised by | Version | Correction Details | Corrected By
The problem isn't with setting NA for one item, it's with setting NA for all items within an area. Try setting NA for each of 1.1.1, 1.1.2, 1.1.3 and 1.1.4 - you'll get the error in the total for 1.1 Scope Initiation and an error in the Category Total for | David Greeen | Issue 1.0 | Corrected bugs raised | Carmelo Costa
Add NA in the pulldown list as a way of indicating not applicable. | David Greeen | Issue 1.0a | Included Suggestion | Carmelo Costa
Automatically generate category assessment (Red/Yellow/Green) but allow reviewer to override. | David Greeen | Issue 1.0a | Included Suggestion | Carmelo Costa
Move Area Selection to First Sheet, Corrected Header and Footer page settings and other improvements. | Terry Ash | Issue 1.2 | Included Suggestion | Carmelo Costa
Add Terms and Abbreviations Sheet | Eiichi Nakamura | Issue 1.2 | Included Suggestion | Carmelo Costa